## Cover
Egyptian Maintenance Company
شركة مصر للصيانة
DAILY REPORT
29-08-2019
Project No. : EPROM ( 226 )
| distribution: |  | 1- EPROM Maintenance Manager
2- EPROM Planning Department
supplementary notes:
9
8
7
6
5
4
| 3 | prepared by |  | Planning department
| 2 | reviewed by |  | Site manager
| 1 | approved by |  | Project manager

## Area 02
` |  |  |  |  | Date: | 03-09-2019
Ser | Permit No. | W-O No. | Area | Tag No. | Operator complain | Problem found | Action Taken | Permit Status | Job Status | ND/D/N
1 |  |  | 2B/14 | 14-LT-004 | AI | No problem | Mass balance was done. | Not-Closed | Completed | ND
2 |  |  | 2B/14 | 14-TE-039 | probation | No problem | Mass balance was done. | Not-Closed | Completed | ND
3 |  |  | 2B/13 | 13-HZ-51 | dismantle | dismantle | Dismantle the following Instruments: 2 pyrometers, 2 flame scanner, Ignitor, impulse line of PT-092, PT-043. | Not-Closed | Completed | ND
2A/05

## Area 04
[5 empty] | Date: | 03-09-2019
S/N | Permit No. | W-O No. | Area | Tag No. | Operator complain | Problem found | Action Taken | Permit Status | Job Status | ND/D/N
1 |  |  | A4/51 | 51-MOV-283 | No feedback |  | Calibrate limit open for the valve, check open and close action found ok. | Not-closed | completed | ND
2 |  |  | A4/52 | 52-PDIT-041A | PMR | PMR | PMR was done | Not-closed | completed | ND
3 |  |  | A4/52 | 52-PDIT-041B | PMR | PMR | PMR was done | Not-closed | completed | ND
4 |  |  | A4/52 | 52-PDIT-04.1C | PMR | PMR | PMR was done | Not-closed | completed | ND
5 |  |  | A4/52 | 52-PDIT-041D | PMR | PMR | PMR was done | Not-closed | completed | ND
6 |  |  | A4/53 | unit 53 | PMR | PMR | Unit survey was done. | Not-closed | completed | ND

## Sheet2 (hidden)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10

## CCTV
Date: 07-08-2019
S/N | Permit No. | W-O No. | Tag No. | Problem Found | Action Taken | Permit Status | Job Status | ND/D/N